Project Planning Phase
Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)
Date
21 October 2022
Team ID
OCEAD56E78F6AD1B7E54
Project Name
Project – Unearthing trends from Linkedin influencers
Maximum Marks
8 Marks
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Use the below template to create product backlog and sprint schedule
Sprint
Functional
User Story
User Story / Task
Story Points
Priority
Team
Requirement (Epic)
Number
Members
Sprint-1
Registration
USN-1
As a user, I can register for the application by
2
High
entering my email, password, and confirming
my password.
USN-2
As a user, I will receive confirmation email once
1
High
Login
I have registered for the application
Sprint-2
USN-3
As a user, I can register for the application
2
Low
Dashboard
through Facebook
USN-4
As a user, I can register for the application
2
Medium
Story
through Gmail
USN-5
As a user, I can log into the application by
1
High
Report
entering email & password

---
Project Tracker, Velocity & Burndown Chart: (4 Marks)
Total Story
Duration
Sprint Start Date
Sprint End Date
Sprint Release Date
Points
(Planned)
Completed (as on
(Actual)
Planned End Date)
20
6 Days
24 Sep 2023
29 Sep 2022
20
29 Oct 2022
20
6 Days
31 Sep 2023
05 Sep 2022
Sprint-3
20
6 Days
07 Oct 2023
12 Oct 2022
Sprint-4
20
6 Days
20 oct 2023
20 Oct 2022
Velocity:
Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per
iteration unit (story points per day)

---
Burndown Chart:
A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such
as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.
https://www.visual-paradigm.com/scrum/scrum-burndown-chart/
https://www.atlassian.com/agile/tutorials/burndown-charts
Reference:
https://www.atlassian.com/agile/project-management
https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software
https://www.atlassian.com/agile/tutorials/epics
https://www.atlassian.com/agile/tutorials/sprints
https://www.atlassian.com/agile/project-management/estimation
https://www.atlassian.com/agile/tutorials/burndown-charts